{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["btrao9n","幸福新农村"],"not_rendered":{"external_links":1,"defined_names":3},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"btrao9n","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true,"flags":["formulas_cached_only"]}

{"sheet":"幸福新农村","index":1,"n_rows":184,"n_cols":15,"rows_kept":184,"merged":[[1,0,1,14],[2,9,2,14],[3,0,6,0],[3,1,6,1],[3,2,6,2],[3,3,6,3],[3,4,6,4],[3,5,6,5],[3,6,6,6],[3,7,6,7],[3,8,3,12],[3,13,6,13],[3,14,6,14],[4,8,6,8],[4,9,4,10],[4,11,6,11],[4,12,6,12],[5,9,6,9],[5,10,6,10],[8,0,8,1],[15,13,17,13],[30,0,30,1],[34,13,35,13],[37,13,38,13],[44,13,45,13],[46,13,47,13],[48,0,48,1],[71,0,71,1],[72,13,73,13],[82,13,83,13],[93,0,93,1],[107,0,107,1],[122,13,123,13],[124,13,125,13],[131,13,133,13],[138,0,138,1],[139,13,140,13],[141,13,142,13],[146,13,147,13],[153,0,153,1],[163,13,164,13],[165,0,165,1],[166,13,167,13],[174,13,176,13],[177,0,177,1]],"flags":["formulas_cached_only"]}
["附件1"]
["2021年鹤山市生态宜居美丽乡村财政奖补项目计划汇总表"]
["填报单位（盖章）：鹤山市农业农村局                   ",{"$nulls":8},"                            填报日期：2021年4月21日"]
["序号","市县","镇（个）","行政村（个）","项目个数（个）","项目名称","类别","建设内容","计划总投资（单位：万元）",{"$nulls":4},"受益人口（人）","备注"]
[{"$nulls":8},"合计","鹤山市补助",null,"村集体经济和社会捐赠","其它财政资金"]
[{"$nulls":9},"市本级美丽乡村标准补助","镇财政补助"]
[]
["全市合计",1,10,82,166,{"$nulls":3},9062.61,2689.06,2381.1,3992.45,null,72379]
["沙坪街道合计",null,1,12,21,{"$nulls":3},1202.77,{"v":347.61000000000007,"d":"347.61"},{"v":342.87999999999994,"d":"342.88"},512.28,null,10309]
[1,"鹤山","沙坪","玉桥",1,"玉桥村委会商铺门口硬底化工程","村道硬底化建设","道路硬底化约（570）平方、114立方",10.6,3.18,3.18,4.24,null,1715]
[2,"鹤山","沙坪","玉桥",2,"玉桥原里新建公厕","农村“厕所革命”","新建公厕约52平方米",28,13.3,14.7,0,null,456]
[3,"鹤山","沙坪","镇南",1,"镇南渠务改造","村容村貌综合整治","新建排水渠长约200米，宽约5米",95,28.5,28.5,38,null,1188]
[4,"鹤山","沙坪","中东西",1,"中东西抛网村富斗独道路改造","村道硬底化建设","道路硬底化约（490）平方",13.3,3.23,3.23,6.84,null,401]
[5,"鹤山","沙坪","汇源",1,"水口经济合作社村容村貌整治","村容村貌综合整治","硬底化、停车位划线、公园等（约2000平方）",100,30,30,40,null,481]
[6,"鹤山","沙坪","赤坎",1,"赤坎大社村容村貌整治","村容村貌综合整治","硬底化（约800平方米）、排水渠覆盖、护栏（约300米）",73.2,21.96,21.96,29.28,null,488]
[7,"鹤山","沙坪","桥氹",1,"木棉岗新建公厕","农村“厕所革命”","新建公厕建筑面积约35平方",22.87,13.3,9.57,0,null,240]
[8,"鹤山","沙坪","桥氹",2,"木棉岗生活管网改造","村容村貌综合整治","更换自来水管（总长约2200米、硬底化约20平方）",60,18,18,24]
[9,"鹤山","沙坪","桥氹",3,"木棉岗新建文化室","公共文化设施建设","新建两层文化室(约470平方）",180,25,25,130]
[10,"鹤山","沙坪","越塘",1,"大朗道路硬底化","村道硬底化建设","长380米，宽10米，共800立方米",160,26.4,26.4,107.2,null,367]
[11,"鹤山","沙坪","越塘",2,"余庆村村容村貌整治","村容村貌综合整治","硬底化（约1700平方）、排水渠（约500米）",49.8,14.94,14.94,19.92,null,365]
[12,"鹤山","沙坪","坡山",1,"坡山唐屋新建公厕","农村“厕所革命”","新建公厕约50平方米",28,13.3,14.7,0,null,294]
[13,"鹤山","沙坪","坡山",2,"坡山东头六队新建公厕","农村“厕所革命”","新建公厕约51平方米",28,13.3,14.7,0,null,176]
[14,"鹤山","沙坪","坡山",3,"坡山东头四队新建公厕","农村“厕所革命”","新建公厕约52平方米",29,13.3,15.7,0,null,204]
[15,"鹤山","沙坪","坡山",4,"坡山南门村容村貌整治","村容村貌综合整治","道路硬底化约990平方米、栏杆约130米、排水管6米等",109,32.7,32.7,43.6,null,773]
[16,"鹤山","沙坪","坡山",5,"坡山村委会公厕改造","农村“厕所革命”","公厕改造约30平方米",12,6,6,0,null,236]
[17,"鹤山","沙坪","坡山",6,"坡山西棠一队新建公厕","农村“厕所革命”","新建公厕约40平方米",23,13.3,9.7,0,null,160]
[18,"鹤山","沙坪","文边",1,"文边村委会村容村貌整治（二）期","村容村貌综合整治","硬底化、运动场、公园等\n（1500平方）",95,28.5,28.5,38,null,857]
[19,"鹤山","沙坪","莺朗",1,"莺朗村委会公厕改造","农村“厕所革命”","公厕改造约20平方米",8,6,2,0,null,769]
[20,"鹤山","沙坪","仓边",1,"仓边村委会亮化工程","村容村貌综合整治","安装路灯约70盏",18,5.4,5.4,7.2,null,847]
[21,"鹤山","沙坪","黄宝坑",1,"黄宝坑坑口村村容村貌整治","村容村貌综合整治","长240米，宽8米，厚20厘米、新建公园",60,18,18,24,null,292]
["雅瑶镇合计",null,1,7,17,{"$nulls":3},1181.4,322.02,322.02,537.3599999999999,null,2552]
[1,"鹤山","雅瑶","南靖",1,"南靖村赤一经济合作社文化楼建设","公共文化设施建设","建设框架结构共两层楼，建筑面积500平方米（含基础）。",150,25,25,100,null,124]
[2,"鹤山","雅瑶","南靖",2,"南靖村赤一经济合作社村道硬底化建设","村道硬底化建设","村内道路100米，宽4米，厚度0.2米，共80立方米",8.8,2.64,2.64,3.52,null,223]
[3,"鹤山","雅瑶","南靖",3,"南靖村赤一经济合作社村容整治建设","村容村貌综合整治","新建村面停车场，长70米，宽8米，厚度0.2米，共112立方米，石提护土等",15.6,4.68,4.68,6.24,null,220]
[4,"鹤山","雅瑶","南靖",4,"南靖村赤三经济合作社村道硬底化建设","村道硬底化建设","村面道路长350米，宽4米，厚0.2米，共280立方米",14,4.2,4.2,5.6000000000000005,null,200]
[5,"鹤山","雅瑶","南靖",5,"南靖村赤三经济合作社健身运动场建设","公共文化设施建设","新建篮球场及健身运动场，长35米，宽22米，厚度0.2米，共154立方米。",15,4.5,4.5,6]
[6,"鹤山","雅瑶","雅瑶",1,"雅瑶村东升经济合作社村道硬地化","村道硬底化建设","村道硬底化：大路长160米、宽6米、厚0.2米；小路长350米、宽4米、厚0.2米，合共体积472立方米（含路基）。",33,9.9,9.9,13.200000000000001,null,180]
[7,"鹤山","雅瑶","昆东",1,"昆东村那水二队经济合作社健身公园","公共文化设施建设","那水二队健身公园，面积500平方",25,7.5,7.5,10,null,280]
[8,"鹤山","雅瑶","昆东",2,"昆东村那水二队经济合作社文化楼建设","公共文化设施建设","那水二队文化楼，框架结构，建筑面积350平方，含基础，厨房",80,24,24,32]
[9,"鹤山","雅瑶","古桥",1,"古桥村早一经济合作社村容整治二期工程","村容村貌综合整治","道路长150米，宽4.5米，约135立方，混凝土墙长100米，约73立方，篮球场祠堂门口广场堵水泥，约190立方",39,11.7,11.7,15.600000000000001,null,190]
[10,"鹤山","雅瑶","古桥",2,"古桥村卢屋经济合作社村容整治二期工程","村容村貌综合整治","混凝土子力墙长200米，高2米，约146立方，路面混凝土长200米，约40立方。道路160米，宽2.5米，约160立方，混凝土子力墙约285立方。",61,18.3,18.3,24.400000000000002,null,175]
[11,"鹤山","雅瑶","建良",1,"建良村大富经济合作社村容整治二期建设工程","村容村貌综合整治","篮球场工程：长32米，宽19米，合计约115立方米；休闲公园约820平方米（含场地硬底化、绿化、填地方砌挡土墙等）村容整治长3100米，共约1500平方米，合计约300立方",104,31.2,31.2,41.599999999999994,null,180]
[12,"鹤山","雅瑶","建良",2,"建良村经济联合社村容整治工程","村容村貌综合整治","村道长约1公里，钢杆路灯20支（7米杆）；环村道路建设工程，250米*4米*0.2米，合计200立方米（砌挡土墙、排水渠封面）",28,8.4,8.4,11.200000000000001,null,220]
[13,"鹤山","雅瑶","建良",3,"建良村坪头经济合作社文化楼建设工程","公共文化设施建设","建设框架结构共两层半楼，建筑面积20平方米（含基础）。",110,25,25,60,null,180]
[14,"鹤山","雅瑶","陈山",1,"陈山村委会村容村貌整治","村容村貌综合整治","广场周边拆除违建530平方，开挖山体252平方，开挖山路388平方，开挖土方降低场地1250平方，清除场地垃圾553平方，捣C25混凝土200厚存道，面积共600平方，捣C25混凝土150厚沟底和乡间小道，面积225平方，捣C20混凝土120厚沟底和乡间小路，面积102平方，砌筑中式栏河总长度246米。",260,78,78,104,null,200]
[15,"鹤山","雅瑶","陈山",2,"陈山坑村文化楼","公共文化设施建设","建设框架结构共两层楼，建筑面积580平方米（含基础）。",98,25,25,48]
[16,"鹤山","雅瑶","隔朗",1,"隔朗村慎思堂前鱼塘周边环境整治","村容村貌综合整治","1、新建1.5米高混凝土挡土墙，长度为125米；2、砌约80米长清水墙围栏，每5米一条水泥柱，水泥板压面，安装1.1米高不锈钢栏杆约45米；3、拆除原有花圃及升旗台，再新设5个绿化树池；4、塘基铺设广场砖约53米长，1.5米宽；5、池塘清淤。",40,12,12,16,null,180]
[17,"鹤山","雅瑶","隔朗",2,"原隔朗小学周边环境整治","村容村貌综合整治","1、设置2个羽毛球场，38个划线停车位，1个滑梯，7套健身器材，6张麻石凳，2套带象棋盘的麻石台凳，2张成品乒乓球桌，1.5米宽面积为222平方米砖砌人行路径，捣制橡胶地面面积为70平方米；2、捣制混凝土路面面积为1494.84平方米；3、新设28个树池；4、原篮球场用围网围起来，长度98米，高2.5米；5、种植绿化面积为830.83平方米，另种植南洋楹3棵。",100,30,30,40]
["桃源镇合计",null,1,10,22,{"$nulls":3},890.84,263.86,263.86,363.12,null,12885]
[1,"鹤山","桃源","富岗",1,"富岗宝鸭塘村蛇头岗至大村道路硬底化工程　","村道硬底化建设","硬底化路面1508平方米",29.9,8.97,8.97,11.96,null,169]
[2,"鹤山","桃源","富岗",2,"富岗东船岗村至火竹焕道路硬底化工程","村道硬底化建设","村道硬底化建设230米，宽5米，厚20公分，230立方米",26.21,7.59,7.59,11.03,null,242]
[3,"鹤山","桃源","龙都",1,"龙都坑溪村第六经济合作社文化室工程","公共文化设施建设","建设一层文化室，建筑面积260平方米",64.64,19.39,19.39,25.86,null,580]
[4,"鹤山","桃源","龙都",2,"龙都坑溪村第六经济合作社新建篮球场工程","公共文化设施建设","硬底化场地1700平方米，覆盖排水渠170米等",39.61,11.88,11.88,15.85,null,580]
[5,"鹤山","桃源","龙都",3,"龙都观溪村村容村貌改造工程","村容村貌综合整治","硬底化场地500平方米，新建排水渠25米等",18.94,5.68,5.68,7.58,null,520]
[6,"鹤山","桃源","龙都",4,"龙都棠都村村庄整治工程 ","村容村貌综合整治","硬底化巷道3000平方米，硬底化排水渠等",76,22.8,22.8,30.4,null,750]
[7,"鹤山","桃源","中心",1,"中心宿坳村文化室工程","公共文化设施建设","建设文化室二层，建筑面积264平方米",62.48,18.74,18.74,24.999999999999996,null,486]
[8,"鹤山","桃源","中心",2,"中心宿坳村茶九坑村道硬底化工程","村道硬底化建设","村道硬底化建设130米，宽4米，厚20公分，需要混凝土104立方米",13.41,3.43,3.43,6.55,null,486]
[9,"鹤山","桃源","中心",3,"中心竹山村文化室工程","公共文化设施建设","建设一层文化室，建筑面积380平方米",70.15,21.05,21.05,28.05,null,130]
[10,"鹤山","桃源","中心",4,"中心竹山村新建公园工程","公共文化设施建设","硬底化场地1500平方米，配套健身设施",51.82,15.55,15.55,20.72,null,130]
[11,"鹤山","桃源","中心",5,"中心竹山村村庄整治工程","村容村貌综合整治","硬底化路面564平方米，新建挡土墙33米，花圃等",48.38,14.51,14.51,19.360000000000007,null,130]
[12,"鹤山","桃源","中心",6,"中心村委会人居环境整治工程（宿坳村、竹山村、中心大村、禾昌合村）","村容村貌综合整治","硬底化约1100平方米，回填土方，安装排水管、不锈钢护栏、种植绿化等",39.19,11.76,11.76,15.67,null,1600]
[13,"鹤山","桃源","蟠龙",1,"蟠龙拱辰村文化室工程   ","公共文化设施建设","两层文化室，建筑面积452平方米",91.68,25,25,41.68000000000001,null,310]
[14,"鹤山","桃源","蟠龙",2,"蟠龙赤瓦村村庄整治工程 ","村容村貌综合整治","硬底化路面1000平方米，新建挡土墙20米，新建排水渠109米及420平方米篮球场等",30.77,9.23,9.23,12.309999999999999,null,85]
[15,"鹤山","桃源","蟠龙",3,"蟠龙村永兴第十六经济合作社村庄整治工程  ","村容村貌综合整治","硬底化路面800平方米，新建排水渠311米、新建挡土墙及不锈钢护栏56米、种植绿化等",41.74,12.52,12.52,16.7,null,270]
[16,"鹤山","桃源","蟠龙",4,"蟠龙村委会环境整治工程","村容村貌综合整治","硬底化道路1100平方米，新建排水渠152米，制作宣传栏等",21.96,6.59,6.59,8.78,null,2800]
[17,"鹤山","桃源","竹蓢",1,"竹蓢岗顶村村庄整治工程","村容村貌综合整治","硬底化路面500平方米，新建排水渠60米等",7.5,2.25,2.25,3,null,107]
[18,"鹤山","桃源","中胜",1,"中胜山鸡坪新村道路硬底化工程","村道硬底化建设","村道硬底化长370米，宽4米，厚20公分，需要296立方混凝土",32.03,9.6,9.6,12.83,null,320]
[19,"鹤山","桃源","甘棠",1,"甘棠白沙边村新建公园工程   ","公共文化设施建设","公园面积1000平方米，种植绿化，砌筑挡土墙和护栏、配套健身设施等",49.84,14.95,14.95,19.94,null,130]
[20,"鹤山","桃源","三富",1,"三富村巷道硬底化工程","村道硬底化建设","圩仔村、大社村、新社村等村巷道硬底化约1300平方米",12.93,3.88,3.88,5.170000000000001,null,1200]
[21,"鹤山","桃源","龙溪",1,"龙溪村委会新建路灯工程（二期）","村容村貌综合整治","新建6米高太阳能路灯54盏，4米高壁挂式太阳能路灯16盏。",21.64,6.49,6.49,8.66,null,1700]
[22,"鹤山","桃源","蟠光",1,"蟠光村文化公园工程","公共文化设施建设","建设公园面积1000米，党建宣传栏、种植绿化等",40.02,12,12,16.020000000000003,null,160]
["龙口镇合计",null,1,12,21,{"$nulls":3},818.6999999999999,296.54,148.27,373.89,null,8258]
[1,"鹤山","龙口","松岗",1,"松岗村村道硬底化","村道硬底化建设","松岗村村道硬底化建设：长1000米，宽4米，厚0.2米，共800立方米。",72,28.8,14.4,28.8,null,900]
[2,"鹤山","龙口","松岗",2,"松岗村公园","公共文化设施建设","松岗村建设竹林公园1000平方米。",20,8,4,8]
[3,"鹤山","龙口","四堡",1,"下藕塘村村道硬底化","村道硬底化建设","下藕塘村村道硬底化建设：长320米，宽3.5米，厚0.2米，共224立方米。",20.15,8.06,4.03,8.06,null,49]
[4,"鹤山","龙口","四堡",2,"昆中村文化楼","公共文化设施建设","昆中村新建文化楼200平方米。",60,24,12,24,null,75]
[5,"鹤山","龙口","协华",1,"龙座村村道硬底化","村道硬底化建设","龙座村村道硬底化建设：长80米，宽5.5米，厚0.2米；长63米，宽3.5米，厚0.2米；长34米，宽4.5米，厚0.2米，共162.7立方米",14.650000000000002,5.86,2.93,5.86,null,541]
[6,"鹤山","龙口","协华",2,"协华旧村篮球场","公共文化设施建设","旧村新建标准篮球场700平方米",20,8,4,8,null,162]
[7,"鹤山","龙口","协华",3,"协新二队文化楼","公共文化设施建设","协新二队新建文化楼300平方米。",80,25,12.5,42.5,null,155]
[8,"鹤山","龙口","青文",1,"西宁村文化楼","公共文化设施建设","西宁村新建文化楼300平方米。",80,25,12.5,42.5,null,164]
[9,"鹤山","龙口","福迳",1,"太平村篮球场","公共文化设施建设","太平村建设标准篮球场700平方米",20,8,4,8,null,546]
[10,"鹤山","龙口","三凤",1,"凤巢一队文化楼","公共文化设施建设","凤巢一队新建文化楼360平方米",96,25,12.5,58.5,null,102]
[11,"鹤山","龙口","三凤",2,"凤巢五队篮球场","公共文化设施建设","凤巢五队新建篮球场630平方米",25,10,5,10,null,280]
[12,"鹤山","龙口","三凤",3,"凤巢五队村庄整治","村容村貌综合整治","凤巢五队村庄综合整治：修建人行绿道，砌石挡土墙，安装护栏等。",70,28,14,28]
[13,"鹤山","龙口","尧溪",1,"平心村村道硬底化","村道硬底化建设","平心村村道硬底化建设：长80米，宽4米，厚0.2米，共64立方米。",6.4,2.3,1.15,2.95,null,961]
[14,"鹤山","龙口","湴蓼",1,"天堂村村道硬底化","村道硬底化建设","天堂村村道硬底化建设：长250米，宽3.5米，厚0.2米，共175立方米。",16,6.3,3.15,6.55,null,849]
[15,"鹤山","龙口","湴蓼",2,"大树坊公园","公共文化设施建设","大树坊建设公园500平方米",21,8.4,4.2,8.4,null,117]
[16,"鹤山","龙口","中七",1,"中七大塘片村庄整治","村容村貌综合整治","中七大塘片村道安装路灯100支，坑尾队安装护栏400米。",35,14,7,14,null,1437]
[17,"鹤山","龙口","三洞",1,"古造村公园","公共文化设施建设","古造村建设公园500平方米",31.5,12.6,6.3,12.6,null,718]
[18,"鹤山","龙口","霄南",1,"坑尾村文化楼","公共文化设施建设","坑尾村新建文化楼280平方米",50,20,10,20,null,323]
[19,"鹤山","龙口","霄南",2,"高水村村道硬底化","村道硬底化建设","高水村村道硬底化建设：长350米，宽3.5米，厚0.2米，共245立方米。",30,8.82,4.41,16.77,null,172]
[20,"鹤山","龙口","霄南",3,"霄南北门村庄整治","村容村貌综合整治","霄南北门村建设污水渠：长280米，深1米，宽1米。",25,10,5,10,null,175]
[21,"鹤山","龙口","五福",1,"五福村庄整治","村容村貌综合整治","五福村修建坳合至楼阁坊村巷道：长165米，宽3米，厚0.2米",26,10.4,5.2,10.4,null,532]
["古劳镇合计",null,1,7,13,{"$nulls":3},891,262.4,262.4,366.2,null,12020]
[1,"鹤山","古劳","茶山",1,"茶山乐安村文化室工程","公共文化设施建设","文化室两层，建筑面积380平方米",65,19.5,19.5,26,null,240]
[2,"鹤山","古劳","茶山",2,"茶山道坪村村容村貌改造工程","村容村貌综合整治","村道硬底化，长300米，建公园，配套健身设施",36,10.799999999999999,10.799999999999999,14.400000000000004,null,270]
[3,"鹤山","古劳","上升",1,"上升村委会村道硬底化（升平八队）工程","村道硬底化建设","村道硬底化，长200米，共700平方米，140立方米。",18,4.62,4.62,8.759999999999998,null,140]
[4,"鹤山","古劳","上升",2,"上升村上升十二队驿站工程","公共文化设施建设","建设休闲驿站一座，建筑面积485平方米",93,25,25,43,null,110]
[5,"鹤山","古劳","双桥",1,"双桥村委会村道硬底化（姓李村至大益村、新墩路口）工程","村道硬底化建设","村道硬底化,1360平方米，厚0.2米，共272立方米",34,8.98,8.98,16.04,null,3200]
[6,"鹤山","古劳","双桥",2,"双桥村容村貌改造（二期）工程","村容村貌综合整治","村内水涉头整治，河涌清淤，周边种植绿化树木，配套休闲小设施等。",150,45,45,60,null,3200]
[7,"鹤山","古劳","连城",1,"连城小江村道硬底化工程","村道硬底化建设","村道硬底化,长600米，宽8米，厚0.2米，共960立方米",100,30,30,40,null,730]
[8,"鹤山","古劳","连南",1,"连南江里村容村貌改造工程","村容村貌综合整治","建公园2000平方米，停车场等",87,26.099999999999998,26.1,34.800000000000004,null,420]
[9,"鹤山","古劳","连南",2,"连南罗江经济合作社小公园工程","公共文化设施建设","建小公园，砌砖墙60米，场地硬底化300平方米，配套休闲设施",20,6,6,8,null,960]
[10,"鹤山","古劳","连南",3,"连南前江村村道硬底化工程","村道硬底化建设","村道硬底化，长800米，宽6米，厚0.2米，共960立方米",100,30,30,40,null,900]
[11,"鹤山","古劳","新星",1,"新星村新和村容村貌改造工程","村容村貌综合整治","建公园，场地硬底化,配套休闲设施",40,12,12,16,null,510]
[12,"鹤山","古劳","新星",2,"新星村洛社党建公园二期工程","公共文化设施建设","建党建公园二期，设置党建元素，筑挡土墙，铺设人行步径、种植绿化树木等",100,30,30,40,null,1020]
[13,"鹤山","古劳","下六",1,"下六禾堂村容村貌改造工程","村容村貌综合整治","建小公园，场地硬底化700平方米，配置休闲设施",48,14.399999999999999,14.4,19.200000000000003,null,320]
["鹤城镇合计",null,1,13,30,{"$nulls":3},1256.8200000000002,342.94999999999993,342.94999999999993,570.92,null,6208]
[1,"鹤山","鹤城","南星",1,"太坪村路灯安装工程","村容村貌综合整治","安装6米高单挑路灯17支、双挑路灯5支，投影灯2套、电壁灯33支",24.3,7.29,7.29,9.720000000000002,null,182]
[2,"鹤山","鹤城","南星",2,"汤屋村村容整治工程","村容村貌综合整治","硬底化1403平方，砌筑毛石挡土墙长19米，镀锌栏杆37米，安装DN400排水管46米，雨水井3座，安装6米高单挑路灯20支、电壁灯2支",53.96,16.19,16.19,21.579999999999995,null,161]
[3,"鹤山","鹤城","南星",3,"五育二队公园路灯安装工程","村容村貌综合整治","安装4米高路灯43盏",21.86,6.56,6.56,8.740000000000002,null,447]
[4,"鹤山","鹤城","南中",1,"鸡心岗村文化楼工程","公共文化设施建设","二层钢筋混凝土框架结构，总建筑面积222.4平方米",55,16.5,16.5,22,null,78]
[5,"鹤山","鹤城","南中",2,"新村村容整治工程","村容村貌综合整治","安装6米高单挑路灯40支、树池8个，花池150平方，车位10个",40,12,12,16,null,274]
[6,"鹤山","鹤城","南洞",1,"上石里二队道路整治工程","村道硬底化建设","扩建路面长468米，宽2米，厚0.2米",20.1,6.03,6.03,8.04,null,123]
[7,"鹤山","鹤城","坑尾",1,"赖屋村村容村貌整治工程","村容村貌综合整治","硬底化865平方，砌筑毛石挡土墙长28米，混凝土护壁2.3立方，安装DN500排水管15米，雨水井2座，清拆危房70平方等",31.06,9.32,9.32,12.419999999999998,null,174]
[8,"鹤山","鹤城","坑尾",2,"灯心坑篮球场工程","公共文化设施建设","新浇捣篮球场28×15米，及周边砼面层共180立方，安装篮球架，球场划线，安装4支球场灯",26.04,7.81,7.81,10.420000000000002,null,72]
[9,"鹤山","鹤城","先锋",1,"大林坪村村容整治工程","村容村貌综合整治","砖砌挡土墙31米，种植桂花5棵、黄榕球40棵、草皮585平方、龙船花50平方；新建村道硬底化面积1195平方等",25.48,7.64,7.64,10.2,null,247]
[10,"鹤山","鹤城","先锋",2,"麦屋村公园工程","公共文化设施建设","硬底化616平方，栽种白银树3棵、桂花8棵、米仔兰22棵、龙船花89.6平方、台湾草273.7平方安装黄蜡石村名牌石，铺装路缘石31.6米等",27.9,8.37,8.37,11.160000000000002,null,192]
[11,"鹤山","鹤城","先锋",3,"西南村村道硬底化工程","村道硬底化建设","长329米，宽3.5米，厚0.2米，共230.3立方米，安装50cm直径波纹管40米",30,7.6,7.6,14.799999999999999,null,38]
[12,"鹤山","鹤城","东坑",1,"金竹村村道硬底化工程","村道硬底化建设","长约430米，宽3.5米，厚0.2米，共301立方米",35,9.93,9.93,15.14,null,142]
[13,"鹤山","鹤城","东坑",2,"东坑坑尾村村道硬底化工程","村道硬底化建设","新建道路长500米，宽5米，及文化室周边硬底化230平方，厚0.2米，合计捣砼共2730平方，546立方",107.48,18.02,18.02,71.44000000000001,null,204]
[14,"鹤山","鹤城","小官田",1,"樟树下村道硬底化工程","村道硬底化建设","长359.25米，宽3.5米，厚0.2米及周边硬底化面积共1670平方，334立方",77.93,11.02,11.02,55.890000000000015,null,454]
[15,"鹤山","鹤城","小官田",2,"老围村公园工程","公共文化设施建设","公园硬底化面积637平方，及周边硬底化104平方，新建花圃长76米，宽1米，花圃内种植龙船花、黄金叶袋苗各38平方，购置健身器材六套等",31.57,9.47,9.47,12.63,null,175]
[16,"鹤山","鹤城","小官田",3,"老围村村道硬底化工程","村道硬底化建设","道路全长314.5米，宽3.5米，厚0.2米，砼共220.15立方，埋6道过路管DN600排水管长，修复暗渠板面修复，新安装水泥盖板",31.59,7.26,7.26,17.07]
[17,"鹤山","鹤城","小官田",4,"杜屋四队道路整治工程","村容村貌综合整治","新建道路长167米，宽3.2米，厚0.2米，砌筑挡土墙80米，周边砌筑花圃",30,9,9,12,null,108]
[18,"鹤山","鹤城","小官田",5,"杜屋四队文化楼工程","公共文化设施建设","新建文化楼一层半，建筑面积250平方",62.78,18.83,18.83,25.120000000000005]
[19,"鹤山","鹤城","小官田",6,"下咀村文化楼工程","公共文化设施建设","新建文化楼一层，建筑面积160平方",48.17,14.45,14.45,19.27,null,262]
[20,"鹤山","鹤城","鹤城",1,"水浪村村道硬底化工程","村道硬底化建设","新建村道硬底化一段长74米，宽3.5米，砼共259平方，一段长185米，宽3.5米，及周边砼面层共1326.3平方，厚0.2米，人行道硬底化143平方，厚0.15米，捣砼共338.51立方",44.82,11.17,11.17,22.479999999999997,null,216]
[21,"鹤山","鹤城","城西",1,"田心村文化楼工程","公共文化设施建设","二层钢筋混凝土框架结构，建筑面积229.5平方米",50.35,15.11,15.11,20.130000000000003,null,101]
[22,"鹤山","鹤城","城西",2,"营信村村容村貌整合整治工程","村容村貌综合整治","新砌砖砌15.22立方，道路硬底化668.5平方，修复检查井2座，安装DN1500排水管40米、砖砌检查井2座，砖砌花场2个",28.46,8.54,8.54,11.380000000000003,null,191]
[23,"鹤山","鹤城","城西",3,"岗叶村村容整治工程","村容村貌综合整治","硬底化面积1000平方，安装雨水井，安装4盏8米高30W LED路灯，新增儿童运动机械3套，成人运动器械10套等",38,11.4,11.4,15.200000000000001,null,105]
[24,"鹤山","鹤城","禾谷",1,"禾谷平安公园","公共文化设施建设","新建鹅卵石人行道长244米，宽1米，安装庭院灯10盏，草坪灯8盏，不锈钢护栏98米，砌筑法制宣传墙15米",56,16.8,16.8,22.400000000000002,null,1170]
[25,"鹤山","鹤城","禾谷",2,"四新村村道硬底化工程","村道硬底化建设","长约500米，宽4米，厚0.2米",43,12.9,12.9,17.200000000000003]
[26,"鹤山","鹤城","禾谷",3,"圩头村村道硬底化工程","村道硬底化建设","长约500米，宽3.5米，厚0.2米",42,11.55,11.55,18.9]
[27,"鹤山","鹤城","坪山",1,"水心洞村文化活动中心及周边整治工程","村容村貌综合整治","新建文化活动中心一层半，建筑面积约150平方，文化活动中心周边整治约700多平方，安装路灯、石凳等",65,19.5,19.5,26,null,656]
[28,"鹤山","鹤城","万和",1,"铁合村篮球场工程","公共文化设施建设","新浇捣篮球场28×15米，安装篮球架，球场划线",15.59,4.68,4.68,6.23,null,118]
[29,"鹤山","鹤城","万和",2,"万和松新村村容村貌综合整治工程","村容村貌综合整治","新建篮球场28×15米，场地硬底化约920平方，新建4套健身器材，安装DN500混凝土个管30米，DN300混凝土管30米，沙井4个，新建5米太阳能路灯2盏，道路硬底化306.8平方，厚0.2米，新建混凝土构造梁，新建钢筋混凝土板约3.8平方，新建护栏73米，安装6米路灯1盏",43.38,13.01,13.01,17.360000000000007,null,70]
[30,"鹤山","鹤城","五星",1,"月山下村村容整治工程","村容村貌综合整治","文化室周边整治1500平方，建设篮球场、健身器材场地、挡土墙30米，文化室周边种植绿化树、硬底化，安装排水管120米、砂井8个等",50,15,15,20,null,248]
["共和镇合计",null,1,8,14,{"$nulls":3},748.2500000000001,220.70000000000002,220.70000000000002,306.85,null,3933]
[1,"鹤山","共和","平汉",1,"平汉排银村广场建设工程","村容村貌综合整治","修建挡土墙，安装不锈钢栏杆40米，安装波纹管33米，雨水口2座，水泥硬底化565平方米，麻石400平方米，广场砖10平方米，路缘石30米，种植牛根草45平方米，砖砌垃圾池等。",49.79,14.94,14.94,19.91,null,820]
[2,"鹤山","共和","平汉",2,"平汉排银村活动中心周边整治工程","村容村貌综合整治","水泥硬底化410平方米，砌筑渠道8.3米，波纹管51米，砖砌花圃等。",12.74,3.82,3.82,5.1]
[3,"鹤山","共和","里元",1,"里元福山村环境美化整治工程","村容村貌综合整治","环村道种植绿化树，花草种植约117.38平方米。",57.87,17.36,17.36,23.15,null,60]
[4,"鹤山","共和","里元",2,"里元村委会福山村巷道硬底化道路工程","村容村貌综合整治","砖砌路缘石102米，挡土墙，花圃，铺设红砖410平方米，单边路缘石322米，不锈钢栏杆16米，下水管道226米，砌筑井11座，雨水口5座，PVC管22米，道路硬底化560平方米。",53.2,15.96,15.96,21.28]
[5,"鹤山","共和","南坑",1,"南坑村委会永丰村示范村改造工程","村容村貌综合整治","道路硬底化1319.2平方米，铺地砖617平方米，砖砌路缘石488.3米，新建水沟9.8米，排水管134.3米，沙井2座，pvc管16.3米，雨水口1座，铺草坪1935.7平方米，种树15株，挡土墙，花圃等。",77.12,23.14,23.14,30.84,null,251]
[6,"鹤山","共和","南坑",2,"南坑村委会旧村示范村改造工程","村容村貌综合整治","道路硬底化473.22平方米，铺蝴蝶砖1000平方米，池塘边墙面亮化，栏杆涂油漆，加固树池，新建花圃，篮球场划线，安装球架，安装健身设施，不锈钢护栏65米，混凝土管30米，雨水口1座，铺广场转142.53平方米，路缘石40米，石凳5张。",57.18,17.15,17.15,22.88,null,148]
[7,"鹤山","共和","泮坑",1,"泮坑长二村文化楼工程","公共文化设施建设","建设二层结构文化室，建筑面积约161平方米。",44.6,13.38,13.38,17.84,null,84]
[8,"鹤山","共和","良庚",2,"共和镇良庚村（仁和）村容村貌整治工程","村容村貌综合整治","新建挡土墙36.7米，新建预埋管43.4米，铺设环保砖375平方米，铺植草砖240平方米，铺种草坪850平方米，道路硬底化1840平方米，车位6个，公园1个，树池，人行道铺砖26.7平方米，路缘石95米，石凳5张，排水渠220米，种植绿化，宣传栏，石凳和石桌。",88.65,26.6,26.6,35.45,null,90]
[9,"鹤山","共和","良庚",3,"良庚仁和村文化楼工程","公共文化设施建设","建设二层结构文化室，建筑面积291.41平方米。",60,18,18,24]
[10,"鹤山","共和","民族",1,"上苑乡村道路硬底化工程","村容村貌综合整治","道路硬底化道路长面积约710平方米，设置明渠，设置波纹管，新建公园一个面积约250平方米。",29.58,8.87,8.87,11.84,null,209]
[11,"鹤山","共和","民族",2,"上苑乡村美丽整治工程","村容村貌综合整治","道路硬底化1150平方米，砌花圃，墙面亮化244.5平方米，新建墙，挡土墙，安装不锈钢栏杆43.5米。",46.93,14.08,14.08,18.77,null,209]
[12,"鹤山","共和","新连",1,"共和镇新连獭山村休闲公园工程","公共文化设施建设","塘边仿木纹水泥护栏212米，青砖筑砌树池50个，砌筑花槽、花圃，砌筑护土墙，混凝土管182米，砖砌出入水口，铺红砖1999平方米，安砌侧(平、缘)石120米，村道铺设混凝土285平方米路面两边砖牙石332米，铺种草皮835平方米，种植绿化树等。",95.95,25,25,45.95,null,156]
[13,"鹤山","共和","来苏",1,"来苏村委会来苏村环村路整治工程","村容村貌综合整治","本工程包含混凝土管62米，砌筑井7座，砖体出水口1座，道路硬底化1024平方米，不锈钢护栏30米，排水渠185米。",57.35,17.21,17.21,22.93,null,1528]
[14,"鹤山","共和","来苏",2,"来苏村委会福临村水渠及环境整治工程","村容村貌综合整治","排水渠清淤和盖板、新建道路，场地平整等。",17.29,5.19,5.19,6.91,null,378]
["址山镇合计",null,1,6,11,{"$nulls":3},1091.93,305.85,305.85,480.23,null,9620]
[1,"鹤山","址山","昆华",1,"林叶文化室建设工程","公共文化设施建设","建设约400平方米",102,25,25,52,null,480]
[2,"鹤山","址山","昆华",2,"沙田文化室建设工程","公共文化设施建设","建设约450平方米",120,25,25,70,null,520]
[3,"鹤山","址山","昆华",3,"仁和横岗村容村貌整治工程","村容村貌综合整治","建设环村路长约200米、宽5米，巷道铺设花圃约325平方米",50,15,15,20,null,350]
[4,"鹤山","址山","新莲",1,"莲塘五队文化楼建设工程","公共文化设施建设","新建文化室约250平方米",62,18.6,18.6,24.8,null,1000]
[5,"鹤山","址山","云新",1,"岗咀村村容村貌整治工程（2期）","村容村貌综合整治","建设3个公园及绿化约2600平方米、村道硬底化约300米，扩宽小桥2米",180,54,54,72,null,300]
[6,"鹤山","址山","云新",2,"二村文化室建设及公园工程　","公共文化设施建设","文化室重建约250平方米，村内公园、装管配套、村内绿化等",100,25,25,50,null,270]
[7,"鹤山","址山","昆联",1,"昆联平沙村容村貌整治工程","村容村貌综合整治","1、平沙村祠堂前鱼塘及四周整治，道路破损修复；2、鱼塘边建设观水平台；3、数目花池及绿化建设等。",159.93,47.98,47.98,63.97,null,2500]
[8,"鹤山","址山","昆中",1,"昆中大道（礼龙线）扩建工程","村道硬底化建设","昆中大道（礼龙线）道路进行扩建，全长2.9公里，路面扩宽至6米，修复破损路面等，铺设混凝土约1996立方米。",220,65.87,65.87,88.26,null,2700]
[9,"鹤山","址山","昆中",2,"昆中村委会龙蟠村村容村貌整治工程","村容村貌综合整治","建设混凝土挡土墙144.64立方米，安装排水管150米，安路灯12套，铺设水泥路面72平方米",49,14.7,14.7,19.6,null,300]
[10,"鹤山","址山","禾南",1,"上黄村容村貌二期整治工程","村容村貌综合整治","新建护栏约300米，排水约250米",22,6.6,6.6,8.8,null,1200]
[11,"鹤山","址山","禾南",2,"上黄村篮球场工程","公共文化设施建设","建设上黄村篮球场，面积约660平方米",27,8.1,8.1,10.8]
["宅梧镇合计",null,1,3,11,{"$nulls":3},603.9,221.72999999999996,119.37,262.79999999999995,null,4612]
[1,"鹤山","宅梧","白水带",1,"宅梧镇白水带钟李村村道硬底化工程","村道硬底化建设","建设村道300m*3.5m*0.2m，共210m³",35,7.56,3.78,23.66,null,499]
[2,"鹤山","宅梧","白水带",2,"宅梧镇白水带竹坑蔡屋村文化室及周边环境整治工程","村容村貌综合整治","建设文化室219㎡，墙、柱面装饰，屋面及防水工程，村道硬底化230㎡，挡土墙17m*3m",75,30,15,30]
[3,"鹤山","宅梧","双龙",1,"宅梧镇双龙村委会大陂村休闲公园","公共文化设施建设","建设600㎡，排水、挡土墙及护栏花圃绿化",85,25,12.5,47.5,null,488]
[4,"鹤山","宅梧","双龙",2,"宅梧镇双龙村委会隆田村公厕工程","农村“厕所革命”","新建30㎡公厕",25,13.3,11.7,0,null,464]
[5,"鹤山","宅梧","双龙",3,"宅梧镇双龙村委会秀坑村公厕工程","农村“厕所革命”","新建30㎡公厕",25,13.3,11.7,0,null,341]
[6,"鹤山","宅梧","双龙",4,"宅梧镇大陂村人居环境建设工程","村容村貌建设","道路硬底化面积647㎡，砌砖面积456.8㎡",51.5,20.6,10.3,20.6,null,488]
[7,"鹤山","宅梧","双龙",5,"宅梧镇双龙村沙下人居环境建设工程","村容村貌建设","建设846㎡公园，排水及护栏花圃绿化",94.4,37.76,18.88,37.76,null,515]
[8,"鹤山","宅梧","堂马",1,"宅梧镇旧堂马小学-佛坑山边道路硬底化工程","村道硬底化建设","建设村道硬底化3240㎡*0.2m，共648m³",76,23.33,11.67,41,null,519]
[9,"鹤山","宅梧","堂马",2,"宅梧镇南门村环村道硬底化工程","村道硬底化建设","建设村道硬底化1622㎡*0.2m，共324.4m³",39,11.68,5.84,21.48,null,1298]
[10,"鹤山","宅梧","堂马",3,"宅梧镇堂马村南门休闲公园工程","公共文化设施建设","建设休闲公园800㎡，排水及护栏花圃绿化",45,18,9,18]
[11,"鹤山","宅梧","堂马",4,"宅梧镇南门村狮化塘环境建设工程","村容村貌建设","新建78米挡土墙，180米护栏，排水及人行道",53,21.2,9,22.8]
["双合镇合计",null,1,4,6,{"$nulls":3},377,105.39999999999999,52.8,218.8,null,1982]
[1,"鹤山","双合","双桥都",1,"双桥都村桥中经济合作社综合文化室建设","公共文化设施建设","新建一间文化楼，长30米，宽20.65米，建筑面积约为522.6平方米",135,25,12.5,97.5,null,508]
[2,"鹤山","双合","双桥都",1,"双桥都村东元经济合作社村容整治","村容村貌综合整治","道路硬底化280米，建钢筋混凝土挡土墙长约70米，宽约0.3米，高约1.8米，护栏140米长，道路两边绿化140米",42,16.8,8.4,16.8,null,603]
[3,"鹤山","双合","合成",1,"合成村长江经济合作社新建公厕","农村“厕所革命”","新建公厕一间约30平方米",20,13.3,6.7,0,null,48]
[4,"鹤山","双合","合成",1,"合成村叶洞经济合作社新建公厕","农村“厕所革命”","新建公厕一间约30平方米",20,13.3,6.7,0,null,120]
[5,"鹤山","双合","泗合",1,"泗合村百块经济合作社文化室建设","公共文化设施建设","新建村文化室约340平方米",130,25,12.5,92.5,null,486]
[6,"鹤山","双合","先庆",1,"先庆村凤村经济合作社村容整治","村容村貌综合整治","道路硬底化约700平方米、路边绿化、鱼塘挡土墙约100米、鱼塘边护栏约100米",30,12,6,12,null,217]